May 2015 Kent Sectional Post Mortem

Attendance: 366.0 tables – down from 395.0 tables in 2014 (-7.3% year-on-year)

Net Income:  Treasurer John has this in work, awaiting final invoices and reimbursables.

Facility rental cost was $3,090 for 4 days including rent and janitorial service ($768/day total).  For comparison, Vasa is $1,095/day, Bothell is $648/day.

Have followed up with Doug Siegert, Kent Commons Manager, to obtain check for refund of $500 damage deposit.  He has confirmed tear down and clean up were fine and deposit will be refunded.

Facility staff was readily available and helpful throughout the weekend.

Space (capacity):  Partnership table and entry purchase table were located out in the hallway to retain as much space as possible for play tables, director table, flyer table and hospitality.  Entire play area capacity (~76 tables) was required for Saturday afternoon session – we scrambled to set up some additional tables.  For future tournaments (especially Forest Ridge and North Seattle College where square footage of the main play area is less than Kent Commons) we should explore availability of nearby additional spaces for potential overflow, taking into account attendance history for the particular tournament (e.g., summer, fall, Feb) to be held at these new sites.

Lighting was fine.  Facility personnel activated overhead electrical receptacle to avoid coffee makers tripping circuit breakers.

Plenty of convenient parking for players – parking was apparently a major problem last time a sectional was held at this facility.  There is also plenty of handy parking for the trailer and board members out back by the loading door.

Restrooms were convenient and kept clean and well supplied throughout the tournament.

Caddies did a good job.  They (and one dad) stayed and were great help during tear down.

No facility kitchen

Wifi available

Wireless microphone was useful

Should allow extra set-up time at first-time venues

Received lots of comments from players about the venue.  Expectedly, comments about location often correlated to proximity to player’s residence.  Comments from several Seattle residents that commute for them was about equivalent to Bothell, where they usually drive around the lake rather than use 520.  Overall, players seemed pleased with the venue’s lighting, parking, and restrooms.  Positive comments about hospitality.  Positive comments about proximity to mall and restaurants across the street.