## Tournaments
Unit 446 Tournament Checklist
| Tournament | St Date | End Date | Notes | Venue (Current) | Venue (Preferred) | DIC | Co-Chair | Co-Chair | Partnership | Sanction# | Bmates | Pre-dupes
2015
| Sweetheart | 2015-02-13 | 2015-02-15 |  | Vasa | Vasa | MattK | Aaron | Romeo | Susan | 1502043 | Myers | Sharon
| I/N | 2015-03-07 | 2015-03-08 |  | N Seattle | N Seattle | Nick | Patti | Susan | Susan | 1503172 | Gram | Sharon
| KO | 2015-05-22 | 2015-05-25 |  | Kent Commons | Kent Commons | MattK | Tim | Mike | Romeo | 1505065 | David | David
| Suntan | 2015-07-24 | 2015-07-26 | OK | Bothell | Bothell | MattK | Kim | Jeff | Susan | 1507037 | Myers | Sharon
| Fall | 2015-10-16 | 2015-10-18 | Change Chair, venue (req sent) | Bothell | Bothell | MattK | Susan | JohnA | Susan | 1510104 | ?? | Sharon
| Fall I/N | 2015-11-07 | 2015-11-08 | Sanction | N Seattle | N Seattle | ?? | Patti |  | Susan |  | ?? | ??
2016
| Sweetheart | 2016-02-26 | 2016-02-28 | Change venue | Vasa | N Seattle | ?? | David |  | Susan |  | ?? | ??
| I/N | 2016-04-16 | 2016-04-17 | OK | N Seattle | N Seattle | ?? | Patti |  | Susan |  | ?? | ??
| KO | 2016-05-27 | 2016-05-30 | OK | Kent Commons | Kent Commons | ?? | David |  | Susan |  | ?? | ??
| Suntan | 2016-07-15 | 2016-07-17 | Confirm dates w/ board, sanction | Forest Ridge | Forest Ridge | ?? | David |  | Susan |  | ?? | ??
| Fall | 2016-10-14 | 2016-10-16 | OK | Bothell | Bothell | ?? | David |  | Susan |  | ?? | ??
| Fall I/N | 2016-11-19 | 2016-11-20 | Date TBC pending 2016 NAPs | N Seattle | N Seattle | ?? | Patti |  | Susan |  | ?? | ??

## Descriptions
Descriptions of work items
Approval Dates
|  | Dates | Have the tournament dates been approved by board and DIC
|  | Location | Has the location been approved by board
|  | Events | Has the tournament list of events been approved by board and DIC
|  | Flyer | Has the flyer been approved by board and DIC
Checklist Items
|  | Venue Contract | Has the contract with the venue been signed
|  | Venue Paid (Due) | Has the venue been paid
|  | Liab Ins (Due) | Has liability insurance been secured
|  | Flyer | Is the flyer available? Then post to website, send email to Sharon (for distribution to clubs), to DW (for SUN) and to the board.
|  | Email Blast | Has an email blast been sent to potential players (if applicable)
|  | Caddies | Are caddies been signed up
|  | Hospitality | Is hospitality in planned and in place
|  | BridgeMates | Have the BridgeMates been rented
|  | Equipment Rental | Has any other necessary equipment been rented (if applicable)
|  | Dup'ed Boards | Are arrangements in place to get dup'ed boards
Week of Tournament
|  | Confirm Setup | Number of people available to do setup
|  | Confirm TearDown | Number of people available to do teardown
|  | Confirm Speakers | Speakers have confirmed (if applicable)
|  | DIC Paperwork | Paperwork needed by directors (list of free plays, entry fees)
|  | Financials | Financials completed by treasurer and DIC

## Venues
U446 Tournament Venues
| Venue Name | Contact | Email | Phone | Address and Dir's |  | Notes
| Bothell | Bev Colegrove | bcolegrove@iuoe302.org | 425 806 0302 | 18701 120th Ave NE | Bothell, WA 98011
Woodinville
| Vasa | Susie Winkowski | sawink@comcast.net | 425-395-4499 | 3549 W. Lake Sammamish Pkwy SE | Bellevue, WA 98008 | Call 30 minutes before leaving facility
| North Seattle College | Amy LaZerte | Amy.LaZerte@seattlecolleges.edu | (206) 934-3600 | 9600 College Way North | Seattle, WA 98103
| Kent Commons | Doug Siegert | dsiegert@kentwa.gov | (253) 856-5000 | 525 4th Ave N. | Kent, WA 98032
| Forest Ridge | Kim Eng | kimen@forestridge.org | 425-765-2417 | 4800 139th Ave SE | Bellevue, WA 98006
Note on F4: David Taylor: From Interstate 405 take exit 24 for NE 195th Street. Head east on 195th St. (This is a right turn if you’re coming from the south and a left turn if you’re coming from the north.) Then take the second right on 120th Ave NE. The site will be on your right in less than half a mile.
Note on F6: David Taylor: From I-90 Eastbound, take Exit #13, and go North on West Lake Sammamish Pkwy SE for about 1¼ miles. Parking lot is on the left.

## Checklist
Unit Tournament Check List (Jan 2015)
Time Line | Task | Responsibility | Description | Contact
12-18 months before event | Review dates with Unit Board | Tournament Coordinator | Using D19-20 Tournament Calendar, select possible dates (see checklist)
12-18 months before event | Review dates with District Coordinator | Tournament Coordinator |  | Matt Koltnow koltwnk@yahoo.ca
12-18 months before event | Secure Venue (see checklist) | Tournament Coordinator/Chair | Copies of signed Contract should be given to Tournament Coordinator, Tournament Chair, Unit Treasurer
12-18 months before event | Sanction Event with ACBL | Tournament Coordinator |  | ACBL TourneyTRAX http://tournaments.acbl.org/UserLogin/
After ACBL approval | Obtain Certificate of Insurance | Tournament Coordinator | Once the Unit Tournament Chair is officially registered with ACBL, you should get a password to login. | http://fs3.formsite.com/acbl/form632296545/index.html
12 months prior | Determine Event Schedule | Tournament Subcommittee
12 months prior | Determine Tournament Chairs | Unit Board
12 months prior | Send schedule to ACBL for approval | Tournament Coordinator |  | ACBL TourneyTRAX http://tournaments.acbl.org/UserLogin/
With ACBL approval & 6 months prior | Create Flyer | Unit Publicity Chair | Make copies for distribution to local clubs in the Unit; give ~200 copies to Matt K for distribution. Request flyer be posted on Seattle, D19* & ACBL websites.
Unit Tournament Check List (July 14 2013)
Time Line | Task | Responsibility | Description | Contact
November of prior year | Arrange Bridgemates | Tournament Coordinator/Chair | We rent bridgemates from John Gram. Send him a schedule for upcoming year to ensure that we have them. | John Gram John.gram@comcast.net
Month prior | Volunteers for Set-Up/Tear Down | Tournament Chair | Arrange for set-up/tear down volunteers
2-3 months prior | Arrange Caddies (check with DIC) | Unit Caddy Chair | Check with DIC for number of caddies. Usually 1 caddy for pair game; 3 for Swiss.
dependent on contract | Venue Payment | Unit Treasurer | Depending on the contract, Unit Treasurer sends payment for venue.
~30-45 days prior | Email Blast | Tournament Coordinator/Chair | Request Email Blast | ACBL <TournamentEmailServices@acbl.org>
~30-45 days prior | Hospitality Chair Equipment Needs | Tournament Chair | Check with Hospitality Chair if need any special equipment
~30-45 days prior | Partnership Chair | Tournament Chair | Check with Partnership Chair that someone will man the desk prior to each session
~30-45 days prior | Equipment Rental | Tournament Chair | Schedule rental of chairs or other items needed for the tournament
month prior | DUP Files | Whoever is duplicating boards | Request DUP files from DIC | Sharon Erwin (as of 4/2013) serwin@clearwire.net
Unit Tournament Check List (July 14 2013)
Time Line | Task | Responsibility | Description | Contact
week prior | Speakers (if applicable) | Tournament Chair | Remind speakers of schedule
week prior | Set-up/Tear Down | Tournament Chair | Remind volunteers
day of tournament | DIC Info | Tournament Coordinator/Chair | When DIC arrives, give copy of info: check cashing policy, entry fee, free play list.
last day of tournament | Tournament Financials | Unit Treasurer/DIC | Unit Treasurer needs to deal with tournament finances with the DIC
last day of tournament | Tear Down | Tournament Chair | Arrange for equiment to be picked up from site | as of 2013, contact David Taylor (davidtay@live.com)
*D19 Flyers | Send to webmaster@d19.org; name the documents using hyphens/underscores instead of spaces and use a descriptive title like U446-2014-February-Flyer

## ACBL #s
ACBL Numbers
| Name | Number | Email address
| Jen Chalfan | J909894 | jenchalfan@gmail.com
| Jeff Ford | R212590 | jeff.ford@gmail.com
| Ray Miller | O132448 | Raymond.Miller@swedish.org
| Susan Cothern | 4348184 | 4susancothern@gmail.com
| Aaron Mohrman | K137186 | mohrman@gmail.com
| Kim Eng | L991512 | KimEn@forestridge.org
| David Taylor | Q450439 | davidtay@live.com
| Patti McCallum | O150284 | pattimcbridge@gmail.com
| Steve Kasner | 9486232 | kasnerbruskland@comcast.net
| Tim White | 4029585 | trkwhite@gmail.com
| Ann Stephens | R381651 | annstephens53@gmail.com
| John Weinberg | M767861 | judgejohn@msn.com
| Ann Romeo | K999846
| Partnerships |  | sbu446partnership@gmail.com

## Archive
Unit 446 Tournament Checklist
[11 empty] | Approval Dates |  |  |  | Checklist Items | [9 empty] | Week of Tournament
| Tournament | St Date | End Date | Notes | Venue | DIC | Co-Chair | Co-Chair | Partnership | Sanction# | Dates | Location | Events | Flyer | Venue Contract (Due) | Venue Paid (Due) | Liab Ins (Due) | Flyer | Email Blast | Caddies | Hospitality | Bridgemates | Equipment Rental | Dup'ed Boards | Confirm Setup | Confirm TearDown | Confirm Speakers | DIC Paperwork | Financials
2014
| Sweetheart | 2014-02-14 | 2014-02-16 |  | Vasa | MattK | Aaron | Ray | Susan | 1402036 | 2014-01-06 | 2014-01-06 | 2014-01-06 | 2014-01-06 | Y | Y | Y | Y |  | Y |  | Y
| I/N | 2014-03-08 | 2014-03-09 |  | Wd'ville | ChrisM | Susan | Patti | Susan | 1403129 | 2014-01-09 | 2014-01-15 | 2014-01-16 | 2014-01-16 | Y | Y | Y | Y |  | Y |  | Y
| KO | 2014-05-23 | 2014-05-25 |  | Bothell | MattK | David | Romeo | Susan | 1405058 | 2014-01-06 | 2014-01-06 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N/A | Y | Y | Y | N/A | Y
| Suntan | 2014-09-05 | 2014-09-07 |  | Bothell | MattK | Jeff | Kim | Susan | 1409056 | 2014-01-06 | 2014-01-06 | Y | Y | Y | Y | Y | Y |  | Y | Y | Y | N/A | Y | Y | Y | N/A | Y | Y
| Fall | 2014-10-31 | 2014-11-02 |  | Vasa | MattK | Steve | Patti | Susan | 1411040 | 2014-01-06 | 2014-01-06 | Y | Y | Y | 2014-09-30 | Y | Y | Y | TBC | Y | Y | N/A | TBC | Y | Y | N/A
Note on W5: David Taylor: DT: Pick up from B'ham McKenzie: Bring from here to OTR
Note on W6: David Taylor: DT: Bring from OTR Sharon: Bring from here to Everett
Note on W7: David Taylor: Gram: Bring units (working)
Note on W8: David Taylor: DT: Bring from Lynnwood (TBC)
Note on W9: David Taylor: TBD