## 2016_09
Fall
Date: | 2016-09-16
Venue: | Kent
Pre-Tournament Tasks | Due | Responsibility | Comp-leted? | Advance Days | Who? | Overdue?
Review dates with Unit Board | 2015-09-17 | David | Yes | 365 | Coordinator | FALSE
Review dates with District Coordinator | 2015-09-17 | David | Yes | 365 | Coordinator | FALSE
Secure Venue | 2015-09-17 | David | Yes | 365 | Coordinator | FALSE
Sanction Event with ACBL | 2015-09-17 | David | Yes | 365 | Coordinator | FALSE
Determine Event Schedule | 2015-09-17 | Board | Yes | 365 | Events | FALSE
Confirm Tournament Chairs | 2015-09-17 | David | Yes | 365 | Coordinator | FALSE
Send schedule to ACBL for approval | 2015-09-17 | David | Yes | 365 | Coordinator | FALSE
Create Flyer | 2016-03-20 | Jen | Yes | 180 | Flyer | FALSE
Print Flyer | 2016-06-18 | Mike | Yes | 90 | Co-Chair | FALSE
Arrange Bridgemates | 2016-06-18 | David | Yes | 90 | Coordinator | FALSE
Distribute Flyer | 2016-07-18 | Mike | Yes | 60 | Co-Chair | FALSE
Update Website | 2016-07-18 | JC | Yes | 60 | Publicity | FALSE
Request Caddy Numbers from DIC | 2016-07-18 | Patti | Yes | 60 | Caddies | FALSE
Send Email Blast | 2016-08-17 | David | Yes | 30 | Coordinator | FALSE
Confirm Availability of Flyers for Next Sectional | 2016-08-17 | JC | Yes | 30 | Publicity | FALSE
Obtain Insurance Cert | 2016-08-17 | David | Yes | 30 | Coordinator | FALSE
Staff Set-Up/Tear Down | 2016-08-17 | Mike | Yes | 30 | Co-Chair | FALSE
Assign Caddies | 2016-08-17 | Patti | Yes | 30 | Caddies | FALSE
Venue Payment | 2016-08-17 | JohnW | Yes | 30 | Treasurer | FALSE
Coordinate with Hospitality Chair | 2016-08-17 | Mike | Yes | 30 | Co-Chair | FALSE
Coordinate with Partnership Chair | 2016-08-17 | Mike | Yes | 30 | Co-Chair | FALSE
Rent Needed Equipment | 2016-08-17 | Mike | N/A | 30 | Co-Chair | FALSE
Find Board Duplicator | 2016-08-17 | David | Yes | 30 | Coordinator | FALSE
Get DUP Files | 2016-08-17 | Sharon | Yes | 30 | BoardDup | FALSE
Remind Speakers | 2016-09-09 | Mike | N/A | 7 | Co-Chair | FALSE
Remind Volunteers | 2016-09-09 | Mike | N/A | 7 | Co-Chair | FALSE
Day of Tournament Tasks
Check in with DIC | 2016-09-16 | Mike | No | 0 | Co-Chair | FALSE
Provide DIC Paperwork | 2016-09-16 | David | No | 0 | Coordinator | FALSE
Provide Caddies Needed List | 2016-09-16 | Patti | No | 0 | Caddies | FALSE
Provide Flyers for Next Sectional | 2016-09-16 | JC | No | 0 | Publicity | FALSE
Pay Caddies | 2016-09-16 | Patti | No | 0 | Caddies | FALSE
Close Financials | 2016-09-16 | JohnW | No | 0 | Treasurer | FALSE
Clean-up / remove equipment | 2016-09-16 | Mike | No | 0 | Co-Chair | FALSE
Details |  |  | Valid Values (don't delete)
Tournament Name | Fall |  | Yes
Date | 2016-09-16 |  | No
Venue | Kent |  | N/A
Co-chair | Mike
Co-chair | Larry
Partnership | Larry
Coordinator | David
Events | Board
Flyer | Jen
Publicity | JC
Caddies | Patti
Treasurer | JohnW
BoardDup | Sharon
Hospitality | AnnR
BridgeMates | David
Oops | Oops | Needed in case there's an error in the formulas above
Formulas:
Due = B45-[Advance Days]
Overdue? = AND([Due]<TODAY(),NOT(OR([Comp-leted?]="Yes",[Comp-leted?]="N/A")))

## 2016_10_IN
Fall I/N
Date: | 2016-10-08
Venue: | N Seattle
Pre-Tournament Tasks | Due | Responsibility | Comp-leted? | Advance Days | Who? | Overdue?
Review dates with Unit Board | 2015-10-09 | David | Yes | 365 | Coordinator | FALSE
Review dates with District Coordinator | 2015-10-09 | David | Yes | 365 | Coordinator | FALSE
Secure Venue | 2015-10-09 | David | Yes | 365 | Coordinator | FALSE
Sanction Event with ACBL | 2015-10-09 | David | Yes | 365 | Coordinator | FALSE
Determine Event Schedule | 2015-10-09 | Board | Yes | 365 | Events | FALSE
Confirm Tournament Chairs | 2015-10-09 | David | Yes | 365 | Coordinator | FALSE
Send schedule to ACBL for approval | 2015-10-09 | David | Yes | 365 | Coordinator | FALSE
Create Flyer | 2016-04-11 | Jen | Yes | 180 | Flyer | FALSE
Print Flyer | 2016-07-10 | Patti | No | 90 | Co-Chair | TRUE
Arrange Bridgemates | 2016-07-10 | David | Yes | 90 | Coordinator | FALSE
Distribute Flyer | 2016-08-09 | Patti | No | 60 | Co-Chair | TRUE
Update Website | 2016-08-09 | JC | Yes | 60 | Publicity | FALSE
Request Caddy Numbers from DIC | 2016-08-09 | Patti | No | 60 | Caddies | TRUE
Send Email Blast | 2016-09-08 | David | No | 30 | Coordinator | TRUE
Confirm Availability of Flyers for Next Sectional | 2016-09-08 | JC | No | 30 | Publicity | TRUE
Obtain Insurance Cert | 2016-09-08 | David | Yes | 30 | Coordinator | FALSE
Staff Set-Up/Tear Down | 2016-09-08 | Patti | No | 30 | Co-Chair | TRUE
Assign Caddies | 2016-09-08 | Patti | No | 30 | Caddies | TRUE
Venue Payment | 2016-09-08 | JohnW | No | 30 | Treasurer | TRUE
Coordinate with Hospitality Chair | 2016-09-08 | Patti | No | 30 | Co-Chair | TRUE
Coordinate with Partnership Chair | 2016-09-08 | Patti | No | 30 | Co-Chair | TRUE
Rent Needed Equipment | 2016-09-08 | Patti | N/A | 30 | Co-Chair | FALSE
Find Board Duplicator | 2016-09-08 | David | No | 30 | Coordinator | TRUE
Get DUP Files | 2016-09-08 | Sharon | No | 30 | BoardDup | TRUE
Remind Speakers | 2016-10-01 | Patti | N/A | 7 | Co-Chair | FALSE
Remind Volunteers | 2016-10-01 | Patti | N/A | 7 | Co-Chair | FALSE
Day of Tournament Tasks
Check in with DIC | 2016-10-08 | Patti | No | 0 | Co-Chair | FALSE
Provide DIC Paperwork | 2016-10-08 | David | No | 0 | Coordinator | FALSE
Provide Caddies Needed List | 2016-10-08 | Patti | No | 0 | Caddies | FALSE
Provide Flyers for Next Sectional | 2016-10-08 | JC | No | 0 | Publicity | FALSE
Pay Caddies | 2016-10-08 | Patti | No | 0 | Caddies | FALSE
Close Financials | 2016-10-08 | JohnW | No | 0 | Treasurer | FALSE
Clean-up / remove equipment | 2016-10-08 | Patti | No | 0 | Co-Chair | FALSE
Details |  |  | Valid Values (don't delete)
Tournament Name | Fall I/N |  | Yes
Date | 2016-10-08 |  | No
Venue | N Seattle |  | N/A
Co-chair | Patti
Co-chair | Susan
Partnership | Larry
Coordinator | David
Events | Board
Flyer | Jen
Publicity | JC
Caddies | Patti
Treasurer | JohnW
BoardDup | Sharon
Hospitality | AnnR
BridgeMates | David
Oops | Oops | Needed in case there's an error in the formulas above
Formulas:
Due = B45-[Advance Days]
Overdue? = AND([Due]<TODAY(),NOT(OR([Comp-leted?]="Yes",[Comp-leted?]="N/A")))

## Reference (hidden)
Pre-Tournament Tasks
Task | Due | Responsibility | Completed? | Advance Days | Overdue? | Contact | Notes
Review dates with Unit Board | 2013-10-31 | Taylor | No | 365 | TRUE
Review dates with District Coordinator | 2013-10-31 | Taylor | No | 365 | TRUE | Matt Koltnow koltwnk@yahoo.ca
Secure Venue | 2013-10-31 | Taylor | No | 365 | TRUE |  | Copies of signed Contract must be given to Tournament Coordinator, Tournament Chair, Unit Treasurer
Sanction Event with ACBL | 2013-10-31 | Taylor | No | 365 | TRUE | ACBL TourneyTRAX http://tournaments.acbl.org/UserLogin/
Obtain Liability Insurance | 2013-10-31 | Taylor | No | 365 | TRUE | MyBB http://forum.acbl.org/index.php | Once the Unit Tournament Chair is officially registered with ACBL, you should get a password to login.
Determine Event Schedule | 2013-10-31 | Tournament Subcommittee | No | 365 | TRUE
Determine Tournament Chairs | 2013-10-31 | Board | No | 365 | TRUE
Send schedule to ACBL for approval | 2013-10-31 | Taylor | No | 365 | TRUE | ACBL TourneyTRAX http://tournaments.acbl.org/UserLogin/
Create Flyer | 2014-05-04 | Chalfan | No | 180 | TRUE
Print Flyer | 2014-08-02 | Taylor | No | 90 | TRUE
Distribute Flyer | 2014-09-01 | Taylor | No | 60 | TRUE |  | Distribute to local clubs in the Unit; give ~200 copies to Matt K for distribution. Request flyer be posted on Seattle, D19* & ACBL websites.
Arrange Bridgemates | 2014-08-02 | Taylor | No | 90 | TRUE | John Gram John.gram@comcast.net | We rent bridgemates from John Gram. Send him a schedule for upcoming year in November to ensure that we have them.
Staff Set-Up/Tear Down | 2014-10-01 | Kasner | No | 30 | TRUE |  | Arrange for set-up/tear down volunteers
Arrange Caddies (check with DIC) | 2014-09-01 | Stephens | No | 60 | TRUE |  | Check with DIC for number of caddies. Usually 1 caddy for pair game; 3 for Swiss.
Venue Payment | 2014-10-01 | White | No | 30 | TRUE |  | Unit Treasurer sends payment for venue, exact date depends on the contract.
Send Email Blast | 2014-10-01 | Taylor | No | 30 | TRUE | ACBL <TournamentEmailServices@acbl.org> | Request Email Blast
Coordinate with Hospitality Chair | 2014-10-01 | Kasner | No | 30 | TRUE |  | Check with Hospitality Chair if need any special equipment
Coordinate with Partnership Chair | 2014-10-01 | Kasner | No | 30 | TRUE |  | Check with Partnership Chair that someone will man the desk prior to each session
Rent Needed Equipment | 2014-10-01 | Kasner | No | 30 | TRUE |  | Schedule rental of chairs or other items needed for the tournament
Find Board Duplicator | 2014-10-01 | Kasner | No | 30 | TRUE |  | Find a volunteer to duplicate boards
Get DUP Files | 2014-10-01 | TBD | No | 30 | TRUE | Sharon Erwin (as of 4/2013) serwin@clearwire.net | Request DUP files from DIC
Remind Speakers | 2014-10-24 | Kasner | No | 7 | TRUE |  | Remind all speakers of their schedule
Remind Volunteers | 41936 | Kasner | No | 7 | TRUE |  | Remind volunteers of times for set-up/tear-down
Tournament Tasks
Check in with DIC | 2014-10-31 | Kasner | No |  | TRUE |  | When DIC arrives, give copy of info: check cashing policy, entry fee, free play list.
Pay caddies | 2014-11-02 | Stephens | No |  | TRUE |  | deal with tournament finances with the DIC' - what is this?
Close financials | 2014-11-02 | White | No |  | TRUE |  | deal with tournament finances with the DIC' - what is this?
Remove Equipment from Site | 41945 | Kasner | No |  | TRUE | as of 2013, contact David Taylor (davidtay@live.com) | Arrange for equiment to be picked up from site
Tournament Info
First Date | 2014-10-31
Last Date | 2014-11-02
Tournament Chair | Kasner
Unit Tournament Coordinator | Taylor
Unit Publicity Chair | Chalfan
Unit Caddy Chair | Stephens
Unit Treasurer | White
Formulas:
Due = B34-[Advance Days]
Overdue? = AND([Due]<TODAY(), NOT([Completed?]="Yes"))